## 4173 General
MONTHLY STATUS REPORT No.: |  | 4 |  | Date : | 2017-11-09
[1] MR shall be referred for furnishing all the below information during fist report. Later as per PR. [2] The below information is required to be submitted to EIL, RPO: Chennai within 1 Week from the date of Receipt of FOA, for all new Orders under EIL's Inspection. |  |  |  | Expected Order Completion Date by Vendor | Vendor's Internal Work Order Ref.
|  |  |  | 2018-03-24 | J 4173
Client: | M/s.IOCL GUJARAT | Project: | BS VI, UNIT - HGU |  |  | Contractual Delivery Date
Vendor: | TITANIUM EQUIPMENT AND ANODE MFG CO LTD |  | Location: | CHENNAI |  | 2018-04-07
FOA No.:
FOA Date: |  | Date of Receipt of FOA by Vendor:
Item | HEAT EXCHANGER - SS |  |  |  | Qty : | 5 NOS
FOA Accepted vide Vendor's Letter No. |  |  |  |  | Date
PO No. | A885/6136/520/PO-173 |  |  |  | Date: | 09.05.2017
PR No. / Rev. No. | A885-602-EE-PR-6136-0173 |  |  |  | Date: | 02.06.2017
Submission Date(s) of: |  |  | Constraints:
[1] "List of Drawings Approval" | Refer the below drawing status |  | [1] Financial Problems: |  | NIL
[2] "List of Items to be sub-ordered" |  |  | [2] Labour Unrest: |  | NIL
[3] QAP | Not Submitted |  | [3] Overloading: |  | NIL
[4] Manufacturing Schedule |  |  | [4] Any Other: |  | NIL
QAP No. : |  |  | Manfacturing Schedule (MS) [Update Monthly]
QAP Rev. No.: | 0
QAP Approved by EIL on:
Raw Material: | Inhouse \ Yet to be sub-ordered \ Sub-ordered and received / not received
Item | Availability Location In-house / Sub-ordered |  | Item |  | Availability Location In-house / Sub-ordered
Tubes - SA213TP321, SA213TP304 | MUMBAI
Forgings- STD- SA182F321, SA182F304 NON STD- SA965F321, SA965F304 | NEW DELHI
Fasteners | Yet to be sub-ordered
SS plates-SA240GR321, SA240GR304 | MUMBAI
CS plates-SA516GR60, SA516GR70 | Yet to be sub-ordered
Gasket | Yet to be sub-ordered
Note(s): | 1. All the Major / Critical Components shall be listed in the Table.
2. If the Drawings will be submitted later, indicate the anticipated submission date in Remarks.
Drawings: |  | * - Anticipated / Actual
Title & Drawing No. | Rev. No. | *Submission Date to EIL Review | Date of Receipt of Drawings from EIL | EIL Review Code | Date of re-submission of Drawings for EIL Review | Any Input specifically required from EIL.
GENERAL ASSEMBLY DETAILS - TEAM-HX-4173A-GA-001 | 1 | 2017-09-20 | 2017-10-13 | R
TUBE SHEET, TUBE BUNDLE, BAFFLE AND COMPONENT DETAILS - TEAM-HX-4173A-FD-001 | 1 | 2017-09-20 | 2017-10-13 | R
NOZZLES, SADDLE AND BILL OF MATERIALS - TEAM-HX-4173A-FD-002 | 1 | 2017-09-20 | 2017-10-13 | R
GASKET DETAILS- TEAM-HX-4173A-FD-003 | 0 | 2017-07-21 | 2017-08-11 | R
NAME PLATE DETAILS - TEAM-HX-4173A-FD-004 | 0 | 2017-07-21 | 2017-08-11 | R
MANDATORY SPARE DETAILS - TEAM-HX-4173A-FD-005 | 0 | 2017-07-21 | 2017-08-11 | R
GENERAL ASSEMBLY DETAILS- TEAM-HX-4173B-GA-001 | 1 | 2017-09-20 | 2017-10-13 | R
TUBE SHEET, TUBE BUNDLE, BAFFLE AND COMPONENT DETAILS- TEAM-HX-4173B-FD-001 | 0 | 2017-07-19 | 2017-08-11 | R
NOZZLES, SADDLE AND BILL OF MATERIALS- TEAM-HX-4173B-FD-002 | 0 | 2017-07-19 | 2017-08-11 | R
GASKET DETAILS - TEAM-HX-4173B-FD-003 | 0 | 2017-07-19 | 2017-08-11 | R
NAME PLATE DETAILS- TEAM-HX-4173B-FD-004 | 0 | 2017-07-19 | 2017-08-11 | R
MANDATORY SPARE DETAILS- TEAM-HX-4173B-FD-005 | 0 | 2017-07-19 | 2017-08-11 | R
GENERAL ASSEMBLY DETAILS- TEAM-HX-4173C-GA-001 | 1 | 2017-09-20 | 2017-10-13 | R
TUBE SHEET, TUBE BUNDLE, BAFFLE AND COMPONENT DETAILS- TEAM-HX-4173C-FD-001 | 0 | 2017-07-19 | 2017-08-11 | R
NOZZLES, SADDLE AND BILL OF MATERIALS - TEAM-HX-4173C-FD-002 | 1 | 2017-09-20 | 2017-10-13 | R
GASKET DETAILS- TEAM-HX-4173C-FD-003 | 0 | 2017-07-19 | 2017-08-11 | R
NAME PLATE DETAILS- TEAM-HX-4173C-FD-004 | 0 | 2017-07-19 | 2017-08-11 | R
MANDATORY SPARE DETAILS- TEAM-HX-4173C-FD-005 | 0 | 2017-07-19 | 2017-08-11 | R
Item | Name of Vendor | Location | S.O. No. ** | S.O. Date | S.O. Delivery Date | Material Receipt Status (Received Quantity so far / Balance Qty expected by)
Tubes - SA213TP321, SA213TP304 | SHUBHLAXMI METALS AND TUBES PVT.LTD. | MUMBAI | 771718401077 | 04.07.2017 | 30.09.2017 | NOT RECEIVED
Forgings- STD- SA182F321, SA182F304 NON STD- SA965F321, SA965F304 | METAL FORGINGS PRIVATE LIMITED | NEWDELHI | 771718401928 | 27.09.2017 | 13.01.2018 | NOT RECEIVED
Fasteners | Yet to be sub-ordered
SS plates-SA240GR321, SA240GR304 | INTER SALES ENTERPRISE & BHANSALI METALS | MUMBAI | 771718401636 | 01.09.2017 & 26.10.2017 | 20.09.2017 & 10.11.2017 | PARTIAL QUANTITY RECEIVED
CS plates-SA516GR60, SA516GR70 | Yet to be sub-ordered
Gasket | Yet to be sub-ordered
** - In case of Imported / "Fully Assembled" Components are involved, mention Import Order No. & Date.
Manufacturing: Please fill details in Next Sheet.
Desptach : Please fill details in Next Sheet.

## 4077-A609 097-II (hidden)
Vendor:M/s |  | TITANIUM EQUIPMENT AND ANODE MFG CO LTD | [5 empty] | FOA No. : | 0 | [10 empty] | Status Report Date: |  | 2017-11-09
Item: |  | HEAT EXCHANGER - SS | [5 empty] | PO No. : | A885/6136/520/PO-173 | [9 empty] | Vendor's Internal Work Order Ref. |  |  | J 4173
FOA Sl# | PR Sl.# | PO Sl.# | Your Line Item No. | Type / Model / Part No. | Tag Number | Size | Rating | H2 Ser vice | IBR | NACE | RT % | Qty As per P.O. in Nos. | Qty Completed in Nos. | Qty Balance in Nos. | Line Item# Partial/ Complete | Raw Material Available Qty in Nos. * | Balance Raw Material expected by (Date) * | Qty of Items Under Assembly | Items Exptd by for EIL or TPI or IBR Inspn by dd/mm/yy | Despatch Details- LR No. | Despatch Details- LR Date | Despatch Details- Transporter Name
A609/097 | A609-103-EE-PR-6038-0097 |  | J4077 | [9 empty] | 0 | 0
0
0
0
Add additional rows, above, if required, as per EIL PR Line Items. | [8 empty] | Total = |  |  | 0 | 0 | 0 |  | 0 |  | 0
* - In case of Imported Components / Fully Assembled Components are ordered, please mention "Import: __".
Fill in either one of "Bulk Item type" or "Fabricated Item type":
For BULK Items: | [15 empty] | For FABRICATION Items:
Milestones: |  |  |  |  | Original Scheduled Date |  | Present Schedule Date |  |  |  | Actual Date |  |  | Qty. |  | Milestones: |  |  | Original Scheduled Date | Present Schedule Date | Actual Date | Qty.
1 | Drawing Submission |  |  |  | 2016-08-23 |  | 2016-08-23 |  |  |  | 30-Aug -16 |  |  |  |  | 1 | Submission of GA Drawings forApproval |  | 23-AUG-16 | 01-SEP-16 | 01-SEP-16
2 | Drawing Approval |  |  |  | 2016-09-22 |  | 2016-09-22 |  |  |  | 30-Aug -17 |  |  |  |  | 2 | Receipt of Approval of Drawings |  | 08-SEP16 | 19-SEP16 | 19-SEP-16
3 | Subordering of Material |  |  |  | 2016-10-15 |  | 2016-10-15 |  |  |  | 15-OCT-16 |  |  |  |  | 3 | Release of sub orders |  | 15-OCT-16 | 15-OCT-16 | 15-OCT-16
4 | Receipt of Material |  |  |  | 2016-12-31 |  | 2016-12-31 | [8 empty] | 4 | Receipt of sub orders |  | 31-12-16 | 30-1-17
5 | Manufacturing |  |  |  | 2017-03-30 |  | 2017-03-30 | [8 empty] | 5 | Long seam welding completion |  | 2016-12-16 | 2017-01-30
6 | Testing and Inspection |  |  |  | 2017-04-15 |  | 2017-04-15 | [8 empty] | 6 | Circ seam welding completion |  | 31-12-16 | 30-1-17
7 | Despatch |  |  |  | 2017-04-30 |  | 2017-04-30 | [8 empty] | 7 | Fabrication completion |  | 25-3-17 | 10-4-17
[16 empty] | 8 | Hydrotest |  | 7-4-17 | 15-4-17
[16 empty] | 9 | Despatch |  | 15-4-17 | 22-4-17
Formulas:
Tag Number = [Tag Number, row above]+30
Rating = [Rating, row above]+30

## 4173 Mfg
Vendor:M/s |  | TITANIUM EQUIPMENT AND ANODE MFG CO LTD | [5 empty] | FOA No. : | [11 empty] | Status Report Date: |  | 2017-11-09
Item: |  | HEAT EXCHANGER | [5 empty] | PO No. : | A885/6136/520/PO-173 | [9 empty] | Vendor'sInternalWork Order Ref. |  |  | J4173
FOA Sl# | PR Sl.# | PO Sl.# | Your Line Item No. | Type / Model / Part No. | Tag Number | Size | Rating | H2 Ser vice | IBR | NACE | RT % | Qty As per P.O. in Nos. | Qty Completed in Nos. | Qty Balance in Nos. | Line Item# Partial/ Complete | Raw Material Available Qty in Nos. * | Balance Raw Material expected by (Date) * | Qty of Items Under Assembly | Items Exptd by for EIL or TPI or IBR Inspn by dd/mm/yy | Despatch Details- LR No. | Despatch Details- LR Date | Despatch Details- Transporter Name
| A885-602-EE-PR-6136-0173 | A885/6136/520/PO-173 | 1.01 | FEED/EFFLUENT EXCHANGER | 602-E-02 A/B | 984 X 5500 |  | N | N | N | 100 | 2 | 0 | 2
| A885-602-EE-PR-6136-0173 | A885/6136/520/PO-173 | 2.01 | DMW PREHEATER | 602-E-108 | 1077 X 7590 |  | N | N | N | 100, 85 | 1 | 0 | 1 |  | 0%
| A885-602-EE-PR-6136-0173 | A885/6136/520/PO-173 | 2.02 | PROCESS CONDENSATE FEED/EFFLUENT EXCHANGER | 602-E-126A/B | 567 X 7330 |  | N | N | N | 100 | 2 | 0 | 2
0
0
[13 empty] | 0 | 0
Add additional rows, above, if required, as per EIL PR Line Items. | [8 empty] | Total = |  |  | 5 | 0 | 5 |  | 0 |  | 0
* - In case of Imported Components / Fully Assembled Components are ordered, please mention "Import: __".
Fill in either one of "Bulk Item type" or "Fabricated Item type":
For BULK Items:
Milestones: |  |  |  |  | Original Scheduled Date |  | Present Schedule Date |  |  |  | Actual Date |  |  | Qty.
1 | Drawing Submission |  |  |  | 2017-05-10 | [5 empty] | 2017-07-21 |  |  | 5 NOS
2 | Drawing Approval |  |  |  | 2017-06-21 | [5 empty] | NOT APPROVED DRAWING IS REVISED
3 | Subordering of Material |  |  |  | 2017-05-26 | [5 empty] | Partial materials ordered and ordering started on 04.07.2017
4 | Receipt of Material |  |  |  | 2017-09-26 | [5 empty] | partial material received
5 | Manufacturing |  |  |  | 2017-06-27
6 | Testing and Inspection |  |  |  | 2018-03-15
7 | Despatch |  |  |  | 2018-04-24
MANUFACTURING STATUS FOR TAG NO: 602-E-02 A/B
MANUFACTURING NOT YET STARTED
MANUFACTURING STATUS FOR TAG NO: 602-E-108
MANUFACTURING NOT YET STARTED
MANUFACTURING STATUS FOR TAG NO: 602-E-126A/B
MANUFACTURING NOT YET STARTED