## Sheet1
# | Phase | WBS.1 | Activity | Resources | Duration (Days) | Dependency | Efforts (Hours) | Cost | Start Date | Finish Date
1 | Required Auditors Approval
2 |  | 5 Auditors Needed
3 |  |  | Interview with Auditors | BA (1) | 3 D |  | 24 | 500 | 2022-10-01 | 2022-10-03
4 |  |  | Interview with Floor Manager | BA (1) | 1 D | 3 | 8 |  | 2022-10-04 | 2022-10-05
5 |  |  | Visit the floor and interact with people | BA (1), Supervisor (1) | 1 D | 4 | 16 |  | 2022-10-06 | 2022-10-07
6 |  |  | Prepare Process Flow Chart | BA (1) | 3 D | 5 | 24 |  | 2022-10-08 | 2022-10-11
7 | Quality process training | Quality process | Quality process instructions
8
9
10 |  | Review | Process instructiions and Flowchart
11 |  | Requirement Approval | Citix software access
12
13
14
15
16
17
18
19