## Sheet1
# | Phase | WBS.1 | Activity | Resources | Duration (Days) | Dependency | Efforts (Hours) | Cost | Start Date | Finish Date
1 | Requirement Understandanding
2 |  | Requirement Collection
3 |  |  | Interview with Operators | BA (1) | 3 D |  | 24
4 |  |  | Interview with Floor Manager | BA (1) | 1 D | 3 | 8
5 |  |  | Visit the floor and interact with people | BA (1), Supervisor (1) | 1 D | 4 | 16
6 |  |  | Prepare Process Flow Chart | BA (1) | 3 D | 5 | 24
7 |  | Prototype
8
9
10 |  | Review
11 |  | Requirement Approval
12
13
14
15
16
17
18
19