## Karthik
# | Phase | WBS.1 | Activity | Resources | Duration (Days) | Dependency | Efforts (Hours) | Cost | Start Date | Finish Date
1 | Requirement Understandanding
2 |  | Requirement Collection
3 |  |  | Interview with Operators | BA (1) | 3 D |  | 24
4 |  |  | Interview with Floor Manager | BA (1) | 1 D | 3 | 8
5 |  |  | Visit the floor and interact with people | BA (1), Supervisor (1) | 1 D | 4 | 16
6 |  |  | Prepare Process Flow Chart | BA (1) | 3 D | 5 | 24
7 |  | Prototype
8
9
10 |  | Review
11 |  | Requirement Approval
12
13 | Work breakdown structure
14 |  | Select engineer
15 |  | Select Building contractor
16 |  | Buy land
17 |  | Arrange for housing loan if required
18
19 | Duration estimation
First we need the building construction blueprint
Get approval from government
Then construction will be started
Should be finished within 6 months from start date
Resource estimation
Based on the buildup area we need cement and other raw material
Need skilled labours to finish the work within 6 months
Labour should work 8 hours per day
Project schedule
After finishing the pre project works such as - blueprint approval, loan arrangement and project will start effective from June 1st 2022 and should be completed by December 31st 2022.
Project cost
|  | Engineer cost | 500000
|  | Purchase of 1200sf land | 1500000
|  | Building contractor cost which includes skilled labours cost and expense | 2000000
|  | Raw material cost | 1500000
|  | Interior cost | 300000
|  | Total cost | 5800000